DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Data Management)

CGIAR Alignment Proposal – Action relating to the ‘Data Management’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Design and implement research data management strategies |  | Aligned data management policies adopted in both ILRI and ICRAF | Priority projects in ICRAF and ILRI fully implementing data management policies | ESA MTP projects using best practice for research data management |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research data management | Workshops, travel, consultants | $25,000 | Staff time and other costs | $84,000 |

Strategy & Objectives of the RMG that relate to the ‘Data Management’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Research data management | - Value of research data limited by not maintaining high quality archives - Inefficient data processing due to poor understanding of management needs - Data and other research documents not linked - Data vulnerable due to poor documentation, inadequate backup, few people who know about any dataset,… - Projects with multiple partners often have no clear data ownership and sharing policy - Technical tools to help in RDM not known or adopted - All the above compounded by distributed research sites and teams | - Develop aligned data management, ownership and access policies - Assist all projects with integrated data management strategies that meet immediate and long term needs - Provide tools and approaches to help technicians, scientists and managers assess and improve their data management - Help centres establish and maintain long term research data archives - Build mechanisms for allowing outreach scientists to be fully integrated into data management practice - Create means of monitoring use of our data and getting feedback |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| RDM (Alignment activities) | Design and implement research data management strategies | - Aligned data management policy (quality, efficiency, preservation) produced. - Technical implementation & documentation of aligned data management policy – 2 workshops (ILRI & ICRAF) for staff to review & comment. - Travel to key other centres to implement system x 2 trips | Muraya Ndiwa Coe Poole | 3 1.5 0.5 0.25 |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Research Data Management | Assist all projects with integrated data management strategies that meet immediate and long term needs | - Integrated data management strategies designed & implemented for ≥ 4 research teams. | Muraya Ndiwa | 2 0.5 |
|  | Tools and approaches to help technicians, scientists and managers assess and improve their data management | - Data Publishing guide produced for ILRI / ICRAF staff & assistance provided on its use x 2 workshops. - Guide to data management in R – or evaluation & recommendation on alternative materials. | Muraya Ndiwa Poole | 2 0.5 0.25 |
|  | Help centres establish and maintain long term research data archives | - Similar to Output in Task 1 above – but focus on data archives, staff leaving/arriving. | Muraya | 1 |
|  | Create means of monitoring use of our data and getting feedback to identify emerging problems | See under implementation of data management policy – more follow-up in 2008. |  |  |
|  | Support to ILRI / ICRAF projects on database design & use | 1. Input into ≥ 4 projects (per location) | Muraya Ndiwa | 1 2 |

Total time (months):

Coe (0.5), Poole (0.5), Muraya (9), Ndiwa (4.5) = 14.5 months