DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – GIS)

CGIAR Alignment Proposal – Action relating to the ‘GIS’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Merge GIS/RS service facilities |  |  | GIS/RS service operating as single ‘shop’ | Spatial analysis demands of ESA MTP projects being met |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| GIS/RS services | Technical assistance, software | $13,000 | Staff time and other costs | $21,000 |

Strategy & Objectives of the RMG that relate to the ‘GIS’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Spatial | - Spatial, temporal and thematic redundancies and gaps in datasets at both local and global levels. - Spatial information not well used when designing and implementing projects - Spatial data products are not always available to users outside the institutes - A wide variety and ever increasing range of software, much of it expensive, is needed in order to process spatial data. - Spatial analysis needs continue to evolve and RMG and other analysts need to keep up - Restrictions on access of data to users outside the two centres due to existing IT policy | - Merging spatial databases and building common catalogues of data holdings to improve quality and delivery and reduce costs - Spatial analysis services to research partners demonstrated and promoted - Using web based GIS as an international public good delivery platform - Rationalise software licensing across the institutes and investigate use of open source alternatives - Diagnosis of the institutes and partners priority capacity needs of which are not met by other suppliers, and development of efficient means of meeting them |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Spatial | Merging spatial databases and building common catalogues of data holdings to improve quality and delivery and reduce costs | - Merged geodatabase rich in EA, Continental and global data – continuous process.(Requires IT assistance to realise the merger due to hardware and inter-connectivity needs.) - Target at least 50-100 datasets | Meshack & Patrick (supervision only) Part-time GIS analyst | 3 months |
|  | Spatial analysis services to research partners demonstrated and promoted | - Increase partnership ≥ 2 in 2007 (SCC-Vi). - Increase size of global spatial community practices and improve variety of spatial tools and information exchange-which is purely listserv where new tools, methods and relevant spatial information are shared through e-mails to ICRAF, ILRI and Key Spatial community of practice.( Meshack please help quantify) | Meshack & Patrick | 1month |
|  | Using web based GIS as an international public good delivery platform | - GIS websites at ILRI & ICRAF harmonized and maintained - GIS portal or GeoNetwork facilities held in one Website | Part-time Web-developer Meshack & Patrick (support) | 2 months |
|  | Rationalise software licensing across the institutes and investigate use of open source alternatives | - Centralized software acquisition and maintenance. - Acquire and promote use of open source software as alternative to commercial-based packages. (Identify at least 1 source and learn its functionality and share knowledge with other users within the institutes) | Patrick & Meshack | 1month |
|  | Diagnosis of the institutes and partners priority capacity needs which are not met by other suppliers, and development of efficient means of meeting them | - Internal and External training options-only user driven through establishing deficiencies within the institutes in the form of capacity to handle emerging challenges in research with the aim of enhancing both technical skills and infrastructure to allow staff to overcome those challenges - Reviewed training manual for different level users both internally and externally. - Establishing one generic training manual for partners that could be modified to fit the needs of a particular client | Patrick & Meshack | 2months |
|  | Support to ILRI & ICRAF projects on the use of spatial information in projects | - Spatial analysis (data, maps and value –added information) to both projects plus ad hoc spatial service requests at cost recovery basis (support at least one project in analysis) - Assisting theme leaders and directors in accessing spatial data for programme and project design and synthesis across projects and regions - Expand to other centres? Yes – at least 1. | Patrick, Addis person & Meshack | 2months |