DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Research Quality Systems)

CGIAR Alignment Proposal – Action relating to the ‘Research Quality Systems’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Revise research planning and implementation procedures to ensure quality |  |  | Aligned procedures for review and documentation in use in ILRI and ICRAF | Common procedures adopted within ESA |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research quality processes | Meetings, travel | $18,000 | Staff time and other costs | $62,000 |

Strategy & Objectives of the RMG that relate to the ‘Research Quality Systems’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Research quality systems | - Research processes often shortcut, particularly initial stages of problem analysis, due to the donor climate and need to respond to opportunities. Lack of realistic assessment of what might be achieved - Ad hoc systems for planning, monitoring and reviewing projects - No standards or common practices for documenting research processes and results - Policies defining institutional approaches to research quality not in place or not followed - Mixed messages to scientists about real priorities – science, development, just bringing in money,… - Everyone is over stretched, hence resistant to anything that looks like extra unproductive work | - Learning from best practice in other industries and institutes - Designing systems for improved planning, monitoring and review. (Harmonised across centres and between planning, monitoring and reviewing) - Designing and using systems which are widely seen as helpful rather than a burden or intrusion - RMG as coach not referee – developing systems with projects, producing guides, training, mentoring, providing advice to senior management - Keeping research and research quality on the agenda of our institutes - Introducing all students attached to the centres to the research process and what it takes to deliver quality results |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Research quality processes (Alignment activities) | Draft procedures based on consultants report | - Draft Protocol Development guidance produced using consultants report. - 4 projects (2 x ILRI, 2 x ICRAF) used to evaluate the procedures. | Coe Poole | 0.5 0.5 |
|  | Facilitated workshops (Nairobi and Addis) for ILRI and ICRAF staff to review and make operational | - Final guidance document produced. - 2 workshops (Nairobi & Addis) used to review and implement guidance. | Coe Poole | 0.5 0.25 |
|  | Travel to key other centres (Indonesia, Mali, India?) for same | - Workshops / consultation at other centres for staff to review and implement guidance. |  | 2008 Activity |
|  | Record keeping systems devised and tested | - Protocols and related documents integrated into data management system for 4 projects (2 x ILRI, 2 x ICRAF) | Coe Muraya | 2 days 0.5 |

| Area | Task Description | Expected Outputs for 2007 | RMG Staff involvement | Time (months) |
| --- | --- | --- | --- | --- |
| Research Quality Systems | Designing systems for improved planning, monitoring and review. (Harmonised across centres and between planning, monitoring and reviewing) | - Current systems in ICRAF revised in light of new strategy and criteria - Systems in ICRAF and ILRI compared, best practice items identified - Options for improvement and alignment presented to senior management | Coe | 0.25 |
|  | Designing and using systems which are widely seen as helpful rather than a burden or intrusion | All work outputs under 1-3 above to follow this approach | Coe | N/A |
|  | RMG as coach not referee – developing systems with projects, producing guides, training, mentoring, providing advice to senior management | - Revised guidelines on implementation of research policies prepared - Assistance to projects, staff, students and partners as requested | Coe Poole | 0.25 0.25 |
|  | Keeping research and research quality on the agenda of our institutes | 1. Contributions to institutional documents, meetings, reports as needed | Coe Poole | 0.25 0.25 |
|  | Introducing all students attached to the centres to the research process and what it takes to deliver quality results | - Revise Induction course and produce pilot online version - Contribute to online and face to face induction course - Contributions on research quality to other training events as requested | Coe Buysse Poole | 0.5 0.5 0.5 |

Total time (months)

Coe (2.5), Poole (1.75), Muraya (0.5), Buysse (0.5) = 5.5 months + 2 days