DRAFT

Programme of Work 2007 – Research Methods Group

(Work Area – Training & Capacity Building)

CGIAR Alignment Proposal – Action relating to the ‘Training & Capacity Building’ issues of the group

| ACTION |  | Milestone for the end of 2006 | Milestone for the end of 2007 | Milestone for the end of 2008 |
| --- | --- | --- | --- | --- |
| Build capacity for quality research services among partners in ESA |  |  | Strategy devised and funding proposals prepared | Funding secures and implementation started |
| AREA | Costs to be covered by the CGIAR | Amount | Costs to be covered by ICRAF and ILRI | Amount |
| Research quality capacity in ESA | Regional consultation, planning meetings , proposal development | $42,000 | Staff and other costs | $54,000 |

| Extent to which 2007 milestone met | Deficiencies | Reasons/comments | Actions for 2008 |
| --- | --- | --- | --- |
| Strategy was devised | No funding proposals prepared | ILRI & ICRAF management decided this should be lead by partners | Continue support for the partners |

Strategy & Objectives of the RMG that relate to the ‘Training & Capacity Building’ issues of the group

| Area | Key Challenges | Approaches |
| --- | --- | --- |
| Regional Capacity | - Capacity of NARS to conceive and implement useful research often limited by experience and resources - Universities use traditional teaching methods that do not develop innovation and critical thinking - Resources for using newer methods not known or used - Capacity building in NARS often limited to demanding provision of training courses and the perceived training needs do not always match the real needs | - Not just focusing on statistics and data management, but covering the whole research process from initial problem analysis to publication of research results and their impact. - Also including topics such as gender, ethics, fraud and misconduct, research as a social process - Not only working with biometricians, lecturers and supervisors, but also directly with a mix of researchers, students and relevant staff of government departments and development NGO’s - Not going into the politics of changing the educational system, university reforms etc. but trying to motivate individuals how to do things differently within the “lousy system” - When working with lecturers and supervisors, stimulate them to think about different ways of teaching and interacting with students - Distribute training and teaching resources in the most appropriate and cost-effective way (as much as possible for free) so that others can use them in their teaching and training. - Also distribute training and teaching resources that exist already but are not widely known. |
| Design & Analysis |  | - Building technical skills of staff, students and partners. - Facilitating access to newer research methods by training, developing guides,…. - Some of the above apply |

| Changed Weaknesses and Threats | Changed strengths and opportunities |
| --- | --- |
| Wim is leaving therefore limited capacity to do external work | Chance to improve our profile by providing quality training |

| Area | Changed: Key Challenges | Changed: Approaches |
| --- | --- | --- |
| Spatial |  |  |

| Area | Task Description | Expected Outputs for 2007 | Achievements | Deficiencies and reasons |
| --- | --- | --- | --- | --- |
| Research quality capacity in ESA (Alignment activities) | Complete, publish and disseminate key paper on teaching research methods | 1. Output as Task Description – “Towards a conceptual framework for teaching research methods” | Draft paper completed Contribution to IAASTD final report. | Paper not finalised and published due to winding up of VVOB project – Wim has had other priorities. |
|  | Regional consultation and planning meetings and an education consultant to prepare a major proposal that will continue after end of VVOB project | 1. RAPSODE project developed through consultation with regional Universities and NARS. Project proposal sent to major donor | Rhapsode planning successful with widespread buy in and project plan developed | Failed to ‘sell’ it to key ICRAF people due to misreading the politics, so whole initiative transferred to partner RUFORUM. Failed to link it to ILRI CAST – can not wake up their interest. |

| Area | Task Description | Expected Outputs for 2007 | Achievements | Deficiencies and reasons |
| --- | --- | --- | --- | --- |
| Regional Capacity | Capacity building to regional libraries | - Restoration of INERA Mulungu library - Books supplied to KEFRI and/or Kisangani library | Done |  |
|  | Training & activities for KEFRI | - Training workshops – representation as Resource person(s) - Publication of technical notes x 3 | Training workshops done. ??? tech notes |  |
|  | Induction Training Workshops | See “Research Quality Systems” Workplan |  |  |
|  | Distribution of training and teaching resources | - Update & maintain research methods resources – website & CD (> 2000 CD’s to be distributed)+ - Development of “Biometrics & Research Methods Teaching Resource”. Options: further case studies, analysis in R - Update manuals for GenStat Discovery 3rd Edition | 1.Cd and website updated and transfered to RUFORUM, along with means of duplicating CDs. 2. Once case study with R developed. Proposal for further funding prepared with John Rowlands 3. GD3 manual updated | The transfer of the research methods cd/web to RUFORUM has left a big gap in our research methods presence. Must be filled by rapidly repopulating new web site. GD3 can be advertised within ILRI/ICRAF once manual is online |
| Training | Building technical skills of staff, students & partners (design, analysis & reporting) | See ‘Analysis & Reporting’ Workplan and ‘Project & Study Design’ Workplan | Training of statistical methods to animal scientists (ASARECA ) Contributed to capacity building of Animal breeders from West Africa (ILRI-SLU) Training of Kabete veterinary labs staff on applications of GIS Training of Vi agroforestry Regional managers on GIS applications. Training of SLP, ILRI-IT, IWMI staff on web based GIS/Advanced GIS applications STATA training to collaborators from Markets theme. Facilitating Training of ILRI GIS user group on Python Script Orientation to statistical methods to new Graduate fellows. Training attached students to the unit. | Access database management training was planned for Market group in Addis but was not done due to non-availability of time in their side Graduate fellows do not come at the same time. |
|  | Facilitating access to newer research methods by training, developing guides,…. | - 2 internal well run courses at ILRI / ICRAF – one charged to cover cost, one free (to estimate potential for internal charging).* - Specialised training courses given ‘on demand’ x 2 (e.g. STATA course to ILRI Theme 3 project) | Initiated needs assessment with positive results | Staff member assigned to lead this work concentrated on the external VVOB project – reasonable, as that paid most of his salary. |