## Minutes
Project | Presentation | number | summary | detail | done
65 | 59 | 1.1 | color contrast | color contrast for the friends of ngong hills website
65 | 59 | 1.2 | Use python to bridge the gap | The gap between Davinci resolve and the output you get.
65 | 59 | 1.3 | Add captions to your videos
65 | 59 | 1.4 | Use python for image compilation and compression
65 | 59 | 1.5 | check on text formatting | The image photo to make it more exciting
65 | 59 | 1.6 | Work with a database for your images
65 | 59 | 1.7 | Rapid editing/sorting under to time pressure
65 | 59 | 1.8 | General template
66 | 59 | 2.1 | Check on the products layout | For the chick joint website
66 | 59 | 2.2 | Optimize the website code | By reducing line of code
66 | 59 | 2.3 | Use actual images for kens website
66 | 59 | 2.4 | Upload the images in the repository with keywords
66 | 59 | 2.5 | Work with the mutall Imagery | To get the images out of the system
66 | 59 | 2.6 | Benchmark on various e-commerce sites available
75 | 60 | 1.1 | For next presenter compare with presentation table
75 | 60 | 1.2 | Create an empty File for current minutes | For the current minutes create an empty file then open editor
75 | 60 | 1.3 | Write queries with only one quote
75 | 60 | 1.4 | Execute workplan with libraries
75 | 60 | 1.5 | Write extract workplan in javascript
75 | 60 | 1.6 | Get the days presenter | Use the intern and presentation table to get the presenter of that date
77 | 60 | 2.1 | Work with Anne to check quality
| 61 | 1.1 | Work on the my hub button |  | 1
| 61 | 1.2 | Comment your css | comment your css this will help you eliminate conflicting css
| 61 | 1.2.1 | Check on which css conflic | For the css, you can try and check which css overrides the previous by checking the latest updates
| 61 | 1.4 | Read them from imagery
89 | 61 | 2.1 | Side hustle/tell us more |  | 1
92 | 61 | 3.1 | create a website to showcase your services
92 | 61 | 3.2 | Web page design | Design a webpage the and illustrates all the services available from your cybercafe.
92 | 61 | 3.3 | Resarch on the cyber problem | To be clear on your cybercafe services, you can do analysis such as problem identification, market research , unique value being added and feasibility study.s
90 | 61 | 4.1 | What is the water consumption for this month
90 | 61 | 4.2 | Electricity bill charges | Is the e bill for this month larger or lower than last
90 | 61 | 4.3 | The interface was pure php.change to js.
88 | 61 | 5.1 | Getting me to grow my project
| 64 | 1.1 | Crone job | Setup a crone job in the co server pertaining the 4 events earlier issued.
| 64 | 1.2 | Test crone job | Add a cron job for each intern birthday and national holidays
| 64 | 1.3 | Set up cron jobs using the do server
| 64 | 2.1 | Add member pictures | add the pictures to match the actual no of memebers
| 64 | 2.2 | enhance the visibility of the members | by (animation,add right margin)
39 | 65 | 1.1 | Work on the autoplay js.
39 | 65 | 1.2 | Add an image to the link | so as users dont think its a virus making them hestitate to clicking them. | 1
39 | 65 | 1.3 | Add feedback section | Add a section where we can get feedback from users. | 1
39 | 65 | 1.4 | Get ideas to improve on next site | which will have the 2023 irua event.
40 | 65 | 2.1 | Have a button for data modelling. | button was created that links metaversio and my application.
40 | 65 | 2.1.1 | Open the mashamba once the button is opened.
40 | 65 | 2.2 | Load Data.
40 | 65 | 2.3.1 | Data upload to the server | Find a way on how you can upload the data using the library to the server. First assume the images are on the server. Next how can we assume its on another computer. | 1
41 | 65 | 3.1 | Model usind the current data | Model usind the current data to areas of improvement. This is with regards to Data Collection.
41 | 65 | 3.4 | Have a good database to support all the data.
43 | 65 | 4.1 | Text difficult to read. Add navigation panel. |  | 1
| 65 | 5.1 | Install Leaflet | On Mr Muraya's Computer and my computer. | 1
| 65 | 5.2 | Try and show a map using the technology. |  | 1
| 65 | 5.3 | Get the coordinates of area of interest | Get the coordinates from PM and layout the area of interest. | 0
| 65 | 7.1 | Copying minutes | Help Mogaka in copying and pasting contribution items.
| 66 | 1.1 | Learn different HTML tags | To help with formating the document. | 1
| 66 | 1.2 | Add a search button on the header |  | 1
| 66 | 1.3 | Learn a bit of Javascript | While managing the document | 1
| 66 | 2.1 | Download softwares used to code in python |  | 1
| 66 | 2.2 | Look for suitable tutorial videos | That can be used to learn the language | 1
| 66 | 2.3 | Use python to query ranix datbase |  | 1
| 66 | 3.1 | Apply to different Japanese Universities |  | 1
| 66 | 3.2 | Emails to admission offices /professors | Write/ answer emails from admission offices/ Professors. | 1
8 | 67 | 1.1 | right align right summaries
8 | 67 | 1.2 | Complete the bottom summary section
| 68 | 1.1 | Multiple selector
| 68 | 1.2 | Search criteria- size,time or location
| 68 | 1.3 | Change the imagery database to a new version
| 68 | 1.4 | Loading more images-php file
| 68 | 1.5 | Separate videos from non videos in imagery
| 68 | 1.6 | Exporting links to websites
| 68 | 2.1 | Hosting the site
| 68 | 2.2 | Take up Android app from mogaka. Get it to work
| 68 | 3.1 | Drag and drop
| 68 | 3.2 | Adding keywords to imagery rapidly
| 68 | 4.1 | Python classes to manage your codes
66 | 68 | 5.1 | Use css for image transition
75 | 69 | 1.1 | Put the strategy in writing | what is the problem, what is the strategy
75 | 69 | 1.2 | Develop execution plan
75 | 69 | 1.3 | Rename minutes to presentation
75 | 69 | 1.4 | Use workplan extraction to learn javascript
| 70 | 1.1 | Other videos related to your work/display random | Research on other videos related to your work/display random
| 70 | 1.2 | Re-design the workplan template from scratch
92 | 70 | 2.1 | create a new business plan
92 | 70 | 2.2 | Design the cybercafe website | Use the workplan template to design the cybercafe website
91 | 70 | 3.1 | start a podcast.
88 | 70 | 4.1 | Learn data management
| 70 | 5.1 | Support your minutes with demonstrations
| 70 | 5.2 | Minutes up to date | check the already done items in your minutes to keep them up to date
| 70 | 5.3 | Learn to do a cleaner folder structure
| 76 | 1.1 | Alert box for search | Add an Alert box that can search out the words RENT and VAT | 1
| 76 | 1.2 | Add my CV at the end of the document |  | 1
| 76 | 1.3 | Add item 0 to the list- Parties to the Agreement |  | 1
| 76 | 1.4 | Add a margin to all different sections | Add a div element to add a margin to all the different sections | 1
| 76 | 1.5 | Agreement template | Encase the agreement conmponents into Munya's template | 1
| 76 | 1.6 | Use Javascript to ensure the GO button works
| 76 | 1.7 | Compile the code
| 76 | 2.1 | Python to query dbase | Use a python function to find out how many cars visited the car park from 1st August 2023 | 1
| 76 | 2.2 | Ensure the python array from the flow data works. |  | 1
| 76 | 3.1 | Reading on Material | Read up on the research material that both Professors have handed to me. | 1
84 | 77 | 1.1 | Add edit and delete buttons to a contribution |  | 1
84 | 77 | 1.2 | Rewrite the query | Rewrite the query starting with a contribution progressing to the presentation | 1
84 | 77 | 1.3 | Indent the contributions |  | 1
84 | 77 | 1.4 | Split contribution to detail and summary | Split the content in the contribution into detail and summary in the data model | 1
| 77 | 2.1 | Registration implementation | Illustrate the implementation of the registration system | 1
| 77 | 3.1 | Work on upload of images to db | Work on getting data to be uploaded to the imagery database from the user
| 77 | 4.1 | Work on the mutall_rental rent query
75 | 78 | 1.1 | Add workplan to database | Convert workplan to minutes and add to the database
75 | 78 | 1.2 | Design the create minutes page | What will the page for create minutes look like?- design the page
| 82 | 1.1 | use metavisio
| 82 | 1.2 | work on migration to the new database
| 82 | 1.3 | option for loading:server side-php file
| 82 | 2.1 | Use fetch | consider using fetch method rather than the template method for mlima panels
| 82 | 2.2 | login to work
| 82 | 3.1 | formulate a plan for the categorization work
| 82 | 3.2 | search panel categorization plan navigation panel
| 82 | 4.1 | An sql query for debit and credit
| 82 | 5.1 | Python classes | Research on grouping python code to classes-indentation also
66 | 82 | 6.1 | Use actual images for kens website
66 | 82 | 6.2 | Mobile view for the site
| 83 | 1.1 | Retrieve agreement details | Retrive agreement contract details from the database. | 1
75 | 84 | 1.1 | Work on the workplan
79 | 84 | 2.1 | Develop kibe's copy method
79 | 84 | 2.2 | Develop water query
| 84 | 3.1 | Mark entities/files with errors in red
| 84 | 3.2 | If you hover on red entity the error should show up
| 84 | 3.3 | Mark attributes that are used for identification with a "*"
| 84 | 3.4 | Attributes that are mandatory should be underlined
| 84 | 3.5 | Relationships should show in a black color- unless they have an error which is shown in red
| 84 | 3.6 | Add smooth drag and drop functionality using Kangara's research
84 | 85 | 1.1 | Work on intergration with sharon's project
84 | 85 | 1.1.1 | Organisation of our folder structure to enable collaboration
84 | 85 | 1.1.2 | Optimisation on the number of times the data from the db is fetched
84 | 85 | 1.1.3 | Extract the dialog from the html document and create it programatically
84 | 85 | 1.1.4 | Work on the deployment issues i.e view.ts and registaration.ts should be in the server
84 | 85 | 1.1.5 | Work on separation of the contribution processes from the presentation class
84 | 85 | 1.2 | Work on the implementation of the edit contribution option
84 | 85 | 1.3 | Work on the concrete implementations of the submit and populate methods of the dialog class
| 85 | 2.1 | Work on the log out implementation in different projects
| 85 | 2.2 | Implement the forgot password option ts
| 85 | 2.2.1 | Implement the forgot password functionality in php
| 85 | 2.3 | Think about the change password option
| 85 | 3.1 | Create and show the dialog that will be used to collect the data
| 85 | 3.2 | Wait for the user to upload then start the data collection from the dialog
| 85 | 3.3 | Continue writing the upload image functionality till each intern is clear on where his method is to be places
| 85 | 3.4 | Investigate on the sutable return type of the various save methods
| 85 | 3.5 | Look at how javascript can handle xml documents to get the appropriate return type from the save operations
| 85 | 4.1 | Sketch the expected results before the query
| 85 | 4.2 | Include the period table to the rent query
| 85 | 5.1 | Look at the mlima database and model the structure to hold data from the user(Imember)
| 85 | 5.2 | Work on opening of the dialog
| 85 | 5.3 | Work on collection of the user inputs from the dialog
| 86 | 1.1 | Add comments on the function/method on the typescript document.
| 86 | 1.2 | Read through the document and identify other id tags that are unique to the individual client.
| 86 | 3.1 | Retrive agreement contract details from the database.
| 86 | 4.1 | Install Metavisuo
40 | 87 | 1.1 | Deploy the application.
40 | 87 | 1.2 | work on the registration system
40 | 87 | 1.3 | uploading of images.
40 | 87 | 1.4 | Link the mutall_users user table with mashamba db. | have a "upload images" button.If its a single document have a way to capture the document.if its multiple documents have a way to upload them all.using a upload input element.specify the folder you want to upload the images in the databaseif there is no folder which you want to have the images in create a new one.
40 | 87 | 1.5 | App Template. | Nelson button shows the docs site. Boundary Conflict resolution.
42 | 87 | 5.1 | Update the documentation | Clarify from the interns which sections of the documentation did not work and update the document the document.
42 | 87 | 5.1 | Database connector for Netbeans.
42 | 87 | 5.3 | How to create a new project in Netbeans.
42 | 87 | 5.4 | Include a video to help in seamless installation for various programs which i have seen are a bit more chalenging for new interns like Xampp.
42 | 87 | 5.4.1 | Apache.
42 | 87 | 5.5 | Add Ds map.
8 | 88 | 1.1 | Complete the bottom summary section
8 | 88 | 1.2 | Add rank summary
8 | 88 | 1.3 | upload to the server the school system(talk to peter)
8 | 88 | 1.4 | Complete the 'edit-score' option - by implementing the save method using the questionnaire library
8 | 88 | 1.5 | Students graduation. - Consider the fact that students graduate from one grade to another after an year by creating new progressions.
10 | 88 | 2.1 | Report progress on bundler Webpack see if it solves the problem we had
10 | 88 | 2.2 | Do the testing with other excel files and report
| 88 | 3.1 | Work on getting the image number from the loop
| 88 | 3.2 | Get the url of the image we come in with
| 88 | 3.3 | Work on getting the alias of the image
| 88 | 3.4 | Work on saving the data in php from DO and other server
| 88 | 4.1 | Sketch the table results on an excel file
| 88 | 4.2 | Include dates 3years and 5 years from now to include the revisions that have been done on the contract
| 89 | 1.1 | work on migration to the new database
| 89 | 1.2 | use the move_upload_file php function
| 89 | 2.1 | create a form for editing images for the members
| 89 | 2.2 | use the dialog library
| 89 | 3.1 | use plain javascript-not interact.js
| 89 | 3.2 | leave just the drop zones
| 89 | 4.1 | An sql query for debit and credit note
| 89 | 5.1 | An sql query for debit and credit note
| 89 | 6.1 | python classes,indentation and methods
66 | 89 | 7.1 | Mobile view for the site
| 90 | 1.1 | Add a search button on the header
| 90 | 1.2 | Make the header colour a little lighter
| 90 | 1.3 | Add a button called, Extract Data, for viewing id tags that have been identified in the document
| 90 | 1.4 | Make a list of all the Id tags identified plus the interchangeable value they represent
| 90 | 1.5 | Use treewalker to list all the highlighted nodes in the makubaliano document
| 90 | 2.1 | Debug the version of Metavisuo that's been installed.
| 90 | 3.1 | Submit LOAs and Placement Preference letters to the embassy of Japan before deadline 5.3
39 | 91 | 1.1 | Have a db to handle the feeback.
39 | 91 | 1.2 | App Template.
39 | 91 |  | have buttons for 2022 an 2023 event. | use the outlook template. show the various page when the buttons are clicked. the 2023 one should show the wordpress 2022 design site. and 2022 to show the current html page.
40 | 91
91

## Workplans2024
intern | project
| name | Comment | problem | plan | outcome
kibe | FitPal |  | Investigaten on firebase log in? What it is and what it does? Simmilar to what simon is doing with sheetjs. Explore the role of webpack in bundling code from different libraries
kibe | KKM |  | How to get data from whats app group whithout a third party. Document the mutall class for working with whats app messeges. Problems with exporting media (with captions)
kibe | Documentation system | karanja, muli | Manage all the documentation we have. Have a method to count words and think of other improvements to the documentation system. Investigate on image hotspots to help in documentation of the user interfaces of our application.
kibe | Image Processing |  | Upgrade and support the mutall imegery dbase. Car number plate extraction. Python for extracting handwritten data form documents to support transcriptions
kibe | Mashamba |  | Publish current titles. Level 2 registration of mashamba users. Migration of the data from the previous data model to the new model. Do research on GIS to help in land disputes and identification of amenities near a parcel of land
kibe | Registration | X | Proceed to register users for the various applications
kibe | KibeHub | X | Investigate how to use react ot create applications. Have all links ot your system avilable on your hub
mogaka | Metavisuo |  | Work on CRUD for data and metadata. Design and write a user intreface documentation for the new version of metavisuo
mogaka | Rentize |  | Get all the rental cte's and ensure they are completed and up to standard
mogaka | Billing |  | Work on acquisition of electricity bills usint an Android platform(Contract for mutall)
mogaka | Chama |  | Work on a chama management system using an Android platform. Identify a chama you are close to also get the diaspora data model (For self Advancement)
mogaka | Registration |  | Work on documentation and mainstreaming of the level 1 registration and also work on level 2 registartion for various projects am working on
mogaka | Tracker |  | Work on planning aspect. Also work on a presentation loading .Define a general template of tracker and populate it with data form the database
muli | Balansys |  | Receipt and stock control project. Continue with bmj stock control. Enter data in the database and then to quickbooks
muli | Rentize |  | Client registration and query consolidation. In conjunction with anne's contract management system
muli | Event planner |  | Learning linux and understanding how the server works
muli | Tracker | mogaka | Managing the financial aspect of the internship e.g, tracking intern loans, Kitchen consumption, monthly stipends. This project will involve kibe with his documentation work and Mogaka who will help with development of the database
muli | Cybercafe | mogaka, karanja | Exploring how to communicate legitimately across origins. (CORS)
muli | Relentless | X | Building and learning the ins and outs of a business. Raising school fees for Diploma. (Self Initiative)
muli | MuliHub | X | showcasing my programming journey and skills
muli | Intern Support |  | Getting interns accustomed to the work environment. Setting up of the intern's computers using kibes documentation
muli | Diploma | X | Doing a course in Software systems and principles at Nibs technical college Nairobi
muli | Mshauri | X | Empowering the youth
muli | Registration |  | Proceed to register users for the various applications
Karanja | Mlima |  | Pick up the pieces of mlima website and make it work together. In mlima the objective should go on the left
Karanja | Chat |  | Getting familiar with sockets. A stand alone application for saving chats. Investigate on monaco editor. Investigate the posibility of using elixir for the sockets
Karanja | Sheetjs |  | Working with sheet js library on balansys. Load the last five list to the balansys database
Karanja | Cyber security | X | Focus on security of data
Karanja | Registration |  | Proceed to register mlima members ( Level 2 registration). Previewing images, factuate , and upload images
muraya | Tabulation |  | Work on a module to tabulate data independent of the source. Use Shule, Oritech and Chama to further the agenda